## Sheet1
Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky
Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
286096 | B4 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 152.0200 | 0.0000 | 21739 | M30 Concrete processing | Cu.Mtrs | 152.0200 | 2524.9237 | 150.001.001.002.002.001.010. | 2524.9237 | Material | 167 | 13913.5600 | C+S GST 18% I/P RD
291287 | B4 FLOOR Pressure Release Pipe Work | No. | 292.0000 | 292.0000 | 28607 | GI Pipe 2" | RMT | 390.0000 | 375.2881 | 150.001.001.002.002.001.015. | 375.2881 | Material | 167 | 12480.0000 | C+S GST 18% I/P RD
286097 | B3 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 397.5100 | 0.0000 | 14236 | M30 Concrete Processing | Cu.Mtrs | 0.0000 | 2524.9237 | 150.001.001.002.002.002.005. | 2524.9237 | Labour | 0 | 0.0000
286097 | B3 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 397.5100 | 0.0000 | 21739 | M30 Concrete processing | Cu.Mtrs | 397.5100 | 2524.9237 | 150.001.001.002.002.002.005. | 2524.9237 | Material | 167 | 36381.9400 | C+S GST 18% I/P RD
286098 | B2 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 269.0600 | 0.0000 | 21739 | M30 Concrete processing | Cu.Mtrs | 22.0000 | 2524.9237 | 150.001.001.002.002.003.002. | 2524.9237 | Material | 167 | 2013.5400 | C+S GST 18% I/P RD
286099 | B1 FLOOR M50 (GGBS) | Cu.Mtrs | 247.0600 | 247.0600 | 14236 | M30 Concrete Processing | Cu.Mtrs | 0.0000 | 2524.9237 | 150.001.001.002.002.004.002. | 2524.9237 | Labour | 0 | 0.0000
286099 | B1 FLOOR M50 (GGBS) | Cu.Mtrs | 247.0600 | 247.0600 | 21739 | M30 Concrete processing | Cu.Mtrs | 247.0600 | 2524.9237 | 150.001.001.002.002.004.002. | 2524.9237 | Material | 167 | 22729.5200 | C+S GST 18% I/P RD
286100 | LG FLOOR M50 (GGBS) | Cu.Mtrs | 238.8200 | 0.0000 | 14236 | M30 Concrete Processing | Cu.Mtrs | 0.0000 | 2524.9237 | 150.001.001.002.002.005.002. | 2524.9237 | Labour | 0 | 0.0000
286100 | LG FLOOR M50 (GGBS) | Cu.Mtrs | 238.8200 | 0.0000 | 21739 | M30 Concrete processing | Cu.Mtrs | 238.8200 | 2524.9237 | 150.001.001.002.002.005.002. | 2524.9237 | Material | 167 | 21971.4400 | C+S GST 18% I/P RD
291223 | IST Material | Per Project | 0.0000 | 0.0000 | 15231 | 25mm PVC BEND | No. | 636.0000 | 7.3475 | 150.001.001.002.006.001. | 7.3475 | Material | 167 | 636.0000 | C+S GST 18% I/P RD
291223 | IST Material | Per Project | 0.0000 | 0.0000 | 20792 | PVC 4 Way Junction Box 25mm | No. | 100.0000 | 19.2627 | 150.001.001.002.006.001. | 19.2627 | Material | 167 | 100.0000 | C+S GST 18% I/P RD
293028 | B4-Conduct Electrical Work | Per Project | 0.0000 | 0.0000 | 15231 | 25mm PVC BEND | No. | 200.0000 | 7.3475 | 150.001.001.005.001.001.001. | 7.3475 | Material | 167 | 200.0000 | C+S GST 18% I/P RD
298704 | Slab Conduct Electrical Work | Per Project | 0.0000 | 0.0000 | 15231 | 25mm PVC BEND | No. | 400.0000 | 7.3475 | 150.001.001.005.001.001.002. | 7.3475 | Material | 167 | 400.0000 | C+S GST 18% I/P RD
299885 | B4 to B1 Conduit Electrical Work | Per Project | 0.0000 | 0.0000 | 15231 | 25mm PVC BEND | No. | 2400.0000 | 7.3475 | 150.001.001.005.001.001.003. | 7.3475 | Material | 167 | 2400.0000 | C+S GST 18% I/P RD
299885 | B4 to B1 Conduit Electrical Work | Per Project | 0.0000 | 0.0000 | 20792 | PVC 4 Way Junction Box 25mm | No. | 1200.0000 | 19.2627 | 150.001.001.005.001.001.003. | 19.2627 | Material | 167 | 1200.0000 | C+S GST 18% I/P RD
295744 | Basement 4 Internal Electrical Work | Per Project | 0.0000 | 0.0000 | 23243 | 2.5mm² x 2core Copper Flexible Cable | Mtrs | 600.0000 | 55.1949 | 150.001.001.005.001.002.001.001. | 55.1949 | Material | 167 | 3000.0000 | C+S GST 18% I/P RD
258653 | Project Electrical Work | Per Project | 0.0000 | 0.0000 | 23243 | 2.5mm² x 2core Copper Flexible Cable | Mtrs | 1000.0000 | 55.1949 | 150.001.001.009.001. | 55.1949 | Material | 167 | 5000.0000 | C+S GST 18% I/P RD
265582 | Project Safety Work | Per Project | 0.0000 | 0.0000 | 30645 | Safety Jacket | No. | 80.0000 | 127.2627 | 150.001.001.009.002.001. | 127.2627 | Material | 167 | 835.2000 | C+S GST 18% I/P RD
290267 | Quality Lab Work | Per Project | 0.0000 | 0.0000 | 11003 | Cube Moulds 150mm x 150mm x 150mm ISI | No. | 12.0000 | 1182.8136 | 150.001.001.009.002.003. | 1182.8136 | Material | 63 | 1008.0000 | V.A.T 12.5%.
287754 | Project Curing Work | Per Project | 0.0000 | 0.0000 | 8310 | ¾" G.I.PIPE | R.Ft | 900.0000 | 39.3898 | 150.001.001.009.008. | 39.3898 | Material | 167 | 2736.1800 | C+S GST 18% I/P RD
268517 | Landscape Work | Per Project | 0.0000 | 0.0000 | 29318 | Foam Sheet | No. | 10.0000 | 1014.02 | 150.001.001.010.003. | 1014.02 | Material | 0 | 0.0000
268517 | Landscape Work | Per Project | 0.0000 | 0.0000 | 23211 | Heliconia Yellow | No. | 100.0000 | 62.54 | 150.001.001.010.003. | 62.54 | Material | 0 | 0.0000
293783 | B3 FLOOR Slab & Beam M40PT(GGBS) | Cu.Mtrs | 773.0000 | 773.0000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 719.1500 | 3349.9237 | 150.001.001.002.002.002.015. | 3349.9237 | Material | 167 | 254171.7800 | C+S GST 18% I/P RD
310496 | B3 FLOOR M40PT(GGBS) - Slab Grade Change | Cu.Mtrs | 25.0000 | 25.0000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.002.020. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
294451 | B2 FLOOR Slab & Beam M40PT(GGBS) | Cu.Mtrs | 933.1000 | 933.1000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.003.006. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
294452 | B1 FLOOR Slab & Beam M40PT(GGBS) | Cu.Mtrs | 795.3800 | 795.3800 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.004.005. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
300280 | LG FLOOR M40PT(GGBS) | Cu.Mtrs | 774.0000 | 774.0000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.005.009. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
301356 | GR FLOOR - PT Slab & Beam - M40PT | Cu.Mtrs | 147.8000 | 147.8000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.006.005. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
301535 | LO 1ST FLOOR M40PT Slab & Beam | Cu.Mtrs | 75.5400 | 75.5400 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.007.007. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
301542 | 1ST FLOOR M40PT - Slab & Beam | Cu.Mtrs | 166.3900 | 166.3900 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.008.007. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
308260 | LO 2ND FLOOR - PT Slab & Beam - M40PT | Cu.Mtrs | 77.5000 | 77.5000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.009.006. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
308267 | 2ND FLOOR PT Slab & Beam - M40PT | Cu.Mtrs | 277.3000 | 277.3000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 0.0000 | 3349.9237 | 150.001.001.002.002.010.007. | 3349.9237 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
308284 | 3RD FLOOR - PT Beam - M40 PT | Cu.Mtrs | 18.0000 | 18.0000 | 28860 | M40 PT Concrete processing | Cu.Mtrs | 18.0000 | 3349.9237 | 150.001.001.002.002.011.010. | 3349.9237 | Material | 167 | 6361.8000 | C+S GST 18% I/P RD
257248 | Temporary Fabrication Work Fencing Work | Per Project | 0.0000 | 0.0000 | 27562 | Self Tapping Screw 1.5" - | No. | 1500.0000 | 2.9407 | 150.001.001.007.009.001.001. | 2.9407 | Material | 167 | 486.0000 | C+S GST 18% I/P RD
260914 | Labour camp material | Per Project | 0.0000 | 0.0000 | 27562 | Self Tapping Screw 1.5" - | No. | 1000.0000 | 2.9407 | 150.001.001.007.010.003. | 2.9407 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
260914 | Labour camp material | Per Project | 0.0000 | 0.0000 | 26395 | SHS 40mm x 40mm | Kgs | 684.0000 | 56.1949 | 150.001.001.007.010.003. | 56.1949 | Material | 167 | 4788.0000 | C+S GST 18% I/P RD
265582 | Project Safety Work | Per Project | 0.0000 | 0.0000 | 13540 | Safety Rubber Hand Gloves | Pair | 25.0000 | 31.1356 | 150.001.001.009.002.001. | 31.1356 | Material | 167 | 75.0000 | C+S GST 18% I/P RD
309454 | Pollution Control Work | Per Project | 0.0000 | 0.0000 | 27562 | Self Tapping Screw 1.5" - | No. | 3225.0000 | 2.9407 | 150.001.001.009.010. | 2.9407 | Material | 167 | 1044.9000 | C+S GST 18% I/P RD
309454 | Pollution Control Work | Per Project | 0.0000 | 0.0000 | 26395 | SHS 40mm x 40mm | Kgs | 1320.0000 | 56.1949 | 150.001.001.009.010. | 56.1949 | Material | 167 | 9038.3000 | C+S GST 18% I/P RD
292634 | Hoarding Work For Marketing | Per Project | 0.0000 | 0.0000 | 27562 | Self Tapping Screw 1.5" - | No. | 3000.0000 | 2.9407 | 150.001.002.004.002. | 2.9407 | Material | 167 | 0.0000 | C+S GST 18% I/P RD