## Sheet1
Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky
Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 14180 | Bolder Excavation | Cu.Mtrs | 1200.0000 | 550 | 150.001.001.002.001.001. | 550 | Labour | 167 | 216.0000 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 13769 | Breaker- | Day | 97.0000 | 1274.2288 | 150.001.001.002.001.001. | 1274.2288 | Labour | 167 | 34.9200 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 14135 | chemical Blasting Bags | No. | 51.0000 | 2200 | 150.001.001.002.001.001. | 2200 | Labour | 167 | 9.1800 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 14470 | Compressor Breaker- | Day | 60.0000 | 4500 | 150.001.001.002.001.001. | 4500 | Labour | 167 | 237.6000 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 6133 | Designing Fees | Job | 1.0000 | 75000 | 150.001.001.002.001.001. | 75000 | Labour | 0 | 0.0000
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 14194 | Excavation in Backfilling | Cu.Mtrs | 1600.0000 | 550 | 150.001.001.002.001.001. | 550 | Labour | 167 | 288.0000 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 13507 | Removing Work | No. | 1.0000 | 200000 | 150.001.001.002.001.001. | 200000 | Labour | 0 | 0.0000
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 14110 | Rock Drilling Work | No. | 2170.0000 | 136.5424 | 150.001.001.002.001.001. | 136.5424 | Labour | 167 | 390.6000 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 2156 | Roller | Day | 3.0000 | 4000 | 150.001.001.002.001.001. | 4000 | Labour | 0 | 0.0000
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 7625 | Transport | No. | 2.0000 | 1000 | 150.001.001.002.001.001. | 1000 | Labour | 0 | 0.0000
291000 | Excavation Dewatering Work | Per Project | 0.0000 | 0.0000 | 8366 | Hose Pipe (L) | No. | 35.0000 | 2500 | 150.001.001.002.001.004. | 2500 | Labour | 0 | 0.0000
307480 | Pilling Design & Consulting | Per Project | 0.0000 | 0.0000 | 6133 | Designing Fees | Job | 1.0000 | 145000 | 150.001.001.002.001.006. | 145000 | Labour | 0 | 0.0000
279685 | Basement 4 Rock Anchoring 32MM | No. | 1340.0000 | 1340.0000 | 11913 | Rock anchoring | No. | 1340.0000 | 450 | 150.001.001.002.002.001.005. | 450 | Labour | 0 | 0.0000
285496 | B4 FLOOR Skin Wall Plum Concrete M15 (GGBS) | Cu.Mtrs | 1422.7300 | 233.0000 | 13554 | Concrete Work | Cu.Mtrs | 1334.1800 | 1765.7458 | 150.001.001.002.002.001.007. | 1765.7458 | Labour | 167 | 240.1600 | C+S GST 18% I/P RD
279687 | Basement 3 Rock Anchoring 32MM | No. | 172.0000 | 172.0000 | 11913 | Rock anchoring | No. | 172.0000 | 450 | 150.001.001.002.002.002.001. | 450 | Labour | 0 | 0.0000
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 12326 | 10mm x 150mm Rebarring | No. | 214.0000 | 156.0763 | 150.001.001.002.002.046.001. | 156.0763 | Labour | 0 | 0.0000
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 13996 | 10mm x 200mm Rebarring | No. | 8.0000 | 146 | 150.001.001.002.002.046.001. | 146 | Labour | 167 | 1.4400 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 12637 | 150mm x 300mm Depth Core cutting | No. | 3.0000 | 780 | 150.001.001.002.002.046.001. | 780 | Labour | 167 | 972.0000 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 13936 | 150mm x 700mm Depth Core cutting | No. | 1.0000 | 1820 | 150.001.001.002.002.046.001. | 1820 | Labour | 167 | 0.1800 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 12939 | 25mm x 300mm Rebarring | No. | 43.0000 | 1374.4153 | 150.001.001.002.002.046.001. | 1374.4153 | Labour | 0 | 0.0000
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 14100 | 300mm x 300mm Depth Core cutting | No. | 1.0000 | 2880 | 150.001.001.002.002.046.001. | 2880 | Labour | 167 | 0.1800 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 14140 | 300mm x 350mm Depth Core cutting | No. | 1.0000 | 3360 | 150.001.001.002.002.046.001. | 3360 | Labour | 167 | 0.1800 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 9320 | 75 x 200mm depth core cutting | No. | 8.0000 | 320 | 150.001.001.002.002.046.001. | 320 | Labour | 0 | 0.0000
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 12639 | 75mm x 300mm Depth Core cutting | No. | 3.0000 | 420 | 150.001.001.002.002.046.001. | 420 | Labour | 167 | 864.0000 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 13769 | Breaker- | Day | 11.0000 | 1500 | 150.001.001.002.002.046.001. | 1500 | Labour | 167 | 3.9600 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 6171 | Electrical Breaker | Day | 4.0000 | 1200 | 150.001.001.002.002.046.001. | 1200 | Labour | 195 | 0.0000 | ZERO 0%
279744 | Basement-4 Raft waterproofing | Sq.Mt | 3421.2600 | 3421.2600 | 2495 | Labour- Pedestal Work | No. | 1384.0000 | 200 | 150.001.001.002.004.001.001. | 200 | Labour | 0 | 0.0000
279744 | Basement-4 Raft waterproofing | Sq.Mt | 3421.2600 | 3421.2600 | 11954 | PRP/Rock anchor /PVC Sleeves Treatment | No. | 1907.0000 | 386.2881 | 150.001.001.002.004.001.001. | 386.2881 | Labour | 0 | 0.0000
279746 | Basement-3 Raft waterproofing | Sq.Mt | 458.5100 | 458.5100 | 11954 | PRP/Rock anchor /PVC Sleeves Treatment | No. | 259.0000 | 350 | 150.001.001.002.004.002.001. | 350 | Labour | 0 | 0.0000
282220 | Basement-2 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 557.5650 | 557.5650 | 9894 | Concrete Joint Treatment | RMT | 173.2500 | 925 | 150.001.001.002.004.003.001. | 925 | Labour | 0 | 0.0000
309421 | Lift Shaft Steel Mesh Making | Per Project | 0.0000 | 0.0000 | 4162 | Fabrication Work | Kgs | 116.7800 | 68.5 | 150.001.001.002.005.001.001. | 68.5 | Labour | 167 | 350.3400 | C+S GST 18% I/P RD
309421 | Lift Shaft Steel Mesh Making | Per Project | 0.0000 | 0.0000 | 6858 | Fabrication Work | No. | 50.0000 | 475 | 150.001.001.002.005.001.001. | 475 | Labour | 0 | 0.0000
310367 | Labour Camp Fabrication Work | Per Project | 0.0000 | 0.0000 | 4162 | Fabrication Work | Kgs | 160.0000 | 20 | 150.001.001.007.010.006. | 20 | Labour | 167 | 480.0000 | C+S GST 18% I/P RD
310367 | Labour Camp Fabrication Work | Per Project | 0.0000 | 0.0000 | 4946 | GATE REPAIRING | Job | 2.0000 | 1400 | 150.001.001.007.010.006. | 1400 | Labour | 0 | 0.0000
312577 | Labour Camp Garbage Collection | Per Project | 0.0000 | 0.0000 | 11611 | Administration Charges | Month | 24.0000 | 385 | 150.001.001.007.010.007. | 385 | Labour | 0 | 0.0000
312577 | Labour Camp Garbage Collection | Per Project | 0.0000 | 0.0000 | 6244 | Wet & Dry Garbage Collection | Month | 24.0000 | 3694.4576 | 150.001.001.007.010.007. | 3694.4576 | Labour | 0 | 0.0000
258653 | Project Electrical Work | Per Project | 0.0000 | 0.0000 | 12596 | Electrical Work | Job | 2.0000 | 132480.3983 | 150.001.001.009.001. | 132480.3983 | Labour | 167 | 0.3600 | C+S GST 18% I/P RD
291278 | Water Tank Fabrication Work | Per Project | 0.0000 | 0.0000 | 4162 | Fabrication Work | Kgs | 542.0000 | 22 | 150.001.001.009.002.004. | 22 | Labour | 167 | 1626.0000 | C+S GST 18% I/P RD
291421 | Steel Testing Work | Per Project | 0.0000 | 0.0000 | 12756 | All Physical Tests of 8 to 32mm Dia Steel | set | 528.0000 | 251.0424 | 150.001.001.009.002.006. | 251.0424 | Labour | 167 | 95.0400 | C+S GST 18% I/P RD
291421 | Steel Testing Work | Per Project | 0.0000 | 0.0000 | 11668 | All Physical Tests of 8-10-12mm. Dia. Bar | No. | 3.0000 | 250 | 150.001.001.009.002.006. | 250 | Labour | 167 | 129.0000 | C+S GST 18% I/P RD
291421 | Steel Testing Work | Per Project | 0.0000 | 0.0000 | 3762 | Chemcial Testing | No. | 259.0000 | 300 | 150.001.001.009.002.006. | 300 | Labour | 0 | 0.0000
293462 | Safety & Quality Work | Per Project | 0.0000 | 0.0000 | 9901 | CTM Machine Calibration 200 Ton | Job | 1.0000 | 4000 | 150.001.001.009.002.007. | 4000 | Labour | 0 | 0.0000
293462 | Safety & Quality Work | Per Project | 0.0000 | 0.0000 | 14248 | FDD By Sand Replacement | No. | 12.0000 | 900 | 150.001.001.009.002.007. | 900 | Labour | 167 | 2.1600 | C+S GST 18% I/P RD
293462 | Safety & Quality Work | Per Project | 0.0000 | 0.0000 | 14249 | Murum Test | No. | 1.0000 | 1000 | 150.001.001.009.002.007. | 1000 | Labour | 167 | 0.1800 | C+S GST 18% I/P RD
293462 | Safety & Quality Work | Per Project | 0.0000 | 0.0000 | 2647 | NDT By UPV & Rebound Hammer | No. | 40.0000 | 206.2542 | 150.001.001.009.002.007. | 206.2542 | Labour | 0 | 0.0000
269216 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 4298 | Chamber cover | No. | 2.0000 | 1250 | 150.001.001.009.003. | 1250 | Labour | 0 | 0.0000
269216 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 4162 | Fabrication Work | Kgs | 727.0000 | 15 | 150.001.001.009.003. | 15 | Labour | 167 | 1962.9000 | C+S GST 18% I/P RD
269216 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 3965 | Fabrication Work | Sq.Ft | 388.0000 | 45 | 150.001.001.009.003. | 45 | Labour | 167 | 1552.0000 | C+S GST 18% I/P RD
269216 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 12026 | Foundation bolt 32mm -1m long | No. | 32.0000 | 600 | 150.001.001.009.003. | 600 | Labour | 0 | 0.0000
286588 | Department/Common Work | Per Project | 0.0000 | 0.0000 | 1464 | Brick Work Mason | No. | 21.0000 | 444.9153 | 150.001.001.009.006.001. | 444.9153 | Labour | 167 | 3.7800 | C+S GST 18% I/P RD
286588 | Department/Common Work | Per Project | 0.0000 | 0.0000 | 1341 | D 1 Labour | Day | 690.0000 | 338.9831 | 150.001.001.009.006.001. | 338.9831 | Labour | 0 | 0.0000
286588 | Department/Common Work | Per Project | 0.0000 | 0.0000 | 6591 | D 1 Labour. | No. | 3860.0000 | 338.9831 | 150.001.001.009.006.001. | 338.9831 | Labour | 195 | 0.0000 | ZERO 0%
286588 | Department/Common Work | Per Project | 0.0000 | 0.0000 | 1340 | D 2 Labour | Day | 90.0000 | 244.0678 | 150.001.001.009.006.001. | 244.0678 | Labour | 0 | 0.0000
286588 | Department/Common Work | Per Project | 0.0000 | 0.0000 | 13472 | D 2 Labour. | No. | 1058.0000 | 244.0678 | 150.001.001.009.006.001. | 244.0678 | Labour | 167 | 380880.0000 | C+S GST 18% I/P RD
309439 | Project Security Services | Per Project | 0.0000 | 0.0000 | 5298 | Bouncer | No. | 4.0000 | 1600 | 150.001.001.009.009.001. | 1600 | Labour | 0 | 0.0000
309454 | Pollution Control Work | Per Project | 0.0000 | 0.0000 | 4162 | Fabrication Work | Kgs | 2940.0000 | 9.322 | 150.001.001.009.010. | 9.322 | Labour | 167 | 8820.0000 | C+S GST 18% I/P RD
258427 | New Drain Line for Excise office to back Side | Per Project | 0.0000 | 0.0000 | 2157 | Excavation in soft murum | Cu.Mtrs | 415.0000 | 225 | 150.001.001.010.001. | 225 | Labour | 0 | 0.0000
286585 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 3965 | Fabrication Work | Sq.Ft | 8500.0000 | 22 | 150.001.001.010.004. | 22 | Labour | 167 | 34000.0000 | C+S GST 18% I/P RD
294429 | External Electrical Work | Per Project | 0.0000 | 0.0000 | 12616 | MSEB shut down work | lumsum | 1.0000 | 5000 | 150.001.001.010.005.001.001. | 5000 | Labour | 0 | 0.0000
294429 | External Electrical Work | Per Project | 0.0000 | 0.0000 | 14299 | S&L LT Cable 3.5C 120sq.mm | Mtrs | 125.0000 | 575 | 150.001.001.010.005.001.001. | 575 | Labour | 167 | 22.5000 | C+S GST 18% I/P RD
294429 | External Electrical Work | Per Project | 0.0000 | 0.0000 | 14166 | S&T LT Cable 3.5C 120sq.mm | No. | 2.0000 | 550 | 150.001.001.010.005.001.001. | 550 | Labour | 167 | 0.3600 | C+S GST 18% I/P RD
314875 | STP Rolling Shutter MS Rolling Shutter | Sq.Ft | 0.0000 | 0.0000 | 7625 | Transport | No. | 1.0000 | 1500 | 150.001.001.010.006.003.001. | 1500 | Labour | 0 | 0.0000
270980 | Sales Expenses | Per Project | 0.0000 | 0.0000 | 13527 | Traveling Expenses | Trip | 42.0000 | 3227.1186 | 150.001.002.004.001. | 3227.1186 | Labour | 167 | 90.7200 | C+S GST 18% I/P RD