## Sheet1
Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky | Project :- Hues Of Sky
Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky | Selected Group :- Hues of Sky
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
251817 | Architectural Consultancy Work | Per Project | 0.0000 | 0.0000 | 5667 | Architectural Services | Sq.Ft | 746848.0000 | 12.98 | 150.001.001.001.001.001. | 12.98 | Labour | 167 | 1478759.0400 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 7124 | Bucket | Hour | 29.5000 | 2478 | 150.001.001.002.001.001. | 2478 | Labour | 0 | 0.0000
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 12885 | Excavation Soft & Hard Murum by Bucket | Cu.Mtrs | 10406.8800 | 295 | 150.001.001.002.001.001. | 295 | Labour | 0 | 0.0000
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 1986 | Excavation in hard rock. | Cu.Mtrs | 40842.6490 | 542.8 | 150.001.001.002.001.001. | 542.8 | Labour | 195 | 0.0000 | ZERO 0%
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 15252 | JCB Bucket | Hour | 16.0000 | 1062 | 150.001.001.002.001.001. | 1062 | Labour | 167 | 720.0000 | C+S GST 18% I/P RD
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 11436 | Mini Poclain With Bucket | Hour | 9.5000 | 1062 | 150.001.001.002.001.001. | 1062 | Labour | 0 | 0.0000
258103 | Excavation Work | Cu.Mtrs | 0.0000 | 0.0000 | 1355 | Tractor | Trip | 20.0000 | 1534 | 150.001.001.002.001.001. | 1534 | Labour | 0 | 0.0000
269395 | Tree Plantation Work | Per Project | 0.0000 | 0.0000 | 7124 | Bucket | Hour | 19.0000 | 2478 | 150.001.001.002.001.002. | 2478 | Labour | 0 | 0.0000
286047 | Ramp Excavation Work | Per Project | 0.0000 | 0.0000 | 12885 | Excavation Soft & Hard Murum by Bucket | Cu.Mtrs | 4800.0000 | 295 | 150.001.001.002.001.003. | 295 | Labour | 0 | 0.0000
279537 | Basement 4 Plum Concrete M15 (GGBS) | Cu.Mtrs | 160.4500 | 305.0000 | 1956 | Plum concrete | Cu.Ft | 39405.0600 | 23.6 | 150.001.001.002.002.001.004. | 23.6 | Labour | 167 | 106393.6600 | C+S GST 18% I/P RD
282081 | B4 FLOOR RCC Labour Work | Sq.Ft | 33701.3300 | 33701.3300 | 1179 | Rcc on Area Basis | Sq.Ft | 33701.3300 | 370.52 | 150.001.001.002.002.001.006. | 370.52 | Labour | 0 | 0.0000
285496 | B4 FLOOR Skin Wall Plum Concrete M15 (GGBS) | Cu.Mtrs | 1422.7300 | 233.0000 | 6223 | Shuttering Work | Sq.Mt | 2935.0000 | 1180 | 150.001.001.002.002.001.007. | 1180 | Labour | 0 | 0.0000
286096 | B4 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 152.0200 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 128.0000 | 1050.2 | 150.001.001.002.002.001.010. | 1050.2 | Labour | 0 | 0.0000
293445 | B4 FLOOR Grade Slab Concrete M20 (GGBS) | Cu.Mtrs | 424.0000 | 424.0000 | 14234 | M20 Concrete Processing | Cu.Mtrs | 424.0000 | 1050.2 | 150.001.001.002.002.001.020. | 1050.2 | Labour | 0 | 0.0000
293445 | B4 FLOOR Grade Slab Concrete M20 (GGBS) | Cu.Mtrs | 424.0000 | 424.0000 | 22264 | M20 Concrete processing | Cu.Mtrs | 275.0000 | 1050.2 | 150.001.001.002.002.001.020. | 1050.2 | Material | 167 | 97194.2400 | C+S GST 18% I/P RD
295475 | B4 FLOOR R/Wall Backside Plum M20 (GGBS) | Cu.Mtrs | 80.6200 | 80.6200 | 14234 | M20 Concrete Processing | Cu.Mtrs | 80.6200 | 1050.2 | 150.001.001.002.002.001.021. | 1050.2 | Labour | 0 | 0.0000
295475 | B4 FLOOR R/Wall Backside Plum M20 (GGBS) | Cu.Mtrs | 80.6200 | 80.6200 | 22264 | M20 Concrete processing | Cu.Mtrs | 78.6200 | 1050.2 | 150.001.001.002.002.001.021. | 1050.2 | Material | 167 | 27786.9400 | C+S GST 18% I/P RD
282082 | B3 FLOOR RCC Labour Work | Sq.Ft | 40905.4700 | 40905.4700 | 1179 | Rcc on Area Basis | Sq.Ft | 40905.4700 | 370.52 | 150.001.001.002.002.002.002. | 370.52 | Labour | 0 | 0.0000
282605 | B3 FLOOR Column Concrete M50 (GGBS) M50 | Cu.Mtrs | 425.9320 | 196.6100 | 14242 | M50 Concrete Processing | Cu.Mtrs | 117.1420 | 1050.2 | 150.001.001.002.002.002.003. | 1050.2 | Labour | 0 | 0.0000
286097 | B3 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 397.5100 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 397.5100 | 1050.2 | 150.001.001.002.002.002.005. | 1050.2 | Labour | 0 | 0.0000
290419 | B3 FLOOR Column concrete M50 (GGBS) | Cu.Mtrs | 86.6500 | 86.6500 | 14242 | M50 Concrete Processing | Cu.Mtrs | 86.6500 | 1050.2 | 150.001.001.002.002.002.013. | 1050.2 | Labour | 0 | 0.0000
293783 | B3 FLOOR Slab & Beam M40PT(GGBS) | Cu.Mtrs | 773.0000 | 773.0000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 778.0000 | 1050.2 | 150.001.001.002.002.002.015. | 1050.2 | Labour | 0 | 0.0000
310496 | B3 FLOOR M40PT(GGBS) - Slab Grade Change | Cu.Mtrs | 25.0000 | 25.0000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 25.0000 | 1050.2 | 150.001.001.002.002.002.020. | 1050.2 | Labour | 0 | 0.0000
310654 | B3 FLOOR M20 (GGBS)-Grade Slab | Cu.Mtrs | 41.0000 | 41.0000 | 14234 | M20 Concrete Processing | Cu.Mtrs | 41.0000 | 1050.2 | 150.001.001.002.002.002.021. | 1050.2 | Labour | 0 | 0.0000
310654 | B3 FLOOR M20 (GGBS)-Grade Slab | Cu.Mtrs | 41.0000 | 41.0000 | 22264 | M20 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.002.002.002.021. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
282084 | B2 FLOOR RCC Labour Work | Sq.Ft | 41286.7300 | 41286.7300 | 1179 | Rcc on Area Basis | Sq.Ft | 41286.7300 | 370.52 | 150.001.001.002.002.003.001. | 370.52 | Labour | 0 | 0.0000
286098 | B2 FLOOR R/Wall Pardi M50 (GGBS) | Cu.Mtrs | 269.0600 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 269.0600 | 1050.2 | 150.001.001.002.002.003.002. | 1050.2 | Labour | 0 | 0.0000
294451 | B2 FLOOR Slab & Beam M40PT(GGBS) | Cu.Mtrs | 933.1000 | 933.1000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 933.1000 | 1050.2 | 150.001.001.002.002.003.006. | 1050.2 | Labour | 0 | 0.0000
294494 | B2 FLOOR M50 (GGBS)-Column Concrete | Cu.Mtrs | 433.3600 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 264.0000 | 1050.2 | 150.001.001.002.002.003.009. | 1050.2 | Labour | 0 | 0.0000
282086 | B1 FLOOR RCC Labour Work | Sq.Ft | 31632.0600 | 31632.0600 | 1179 | Rcc on Area Basis | Sq.Ft | 31632.0600 | 370.52 | 150.001.001.002.002.004.001. | 370.52 | Labour | 0 | 0.0000
286099 | B1 FLOOR M50 (GGBS) | Cu.Mtrs | 247.0600 | 247.0600 | 14242 | M50 Concrete Processing | Cu.Mtrs | 247.0600 | 1050.2 | 150.001.001.002.002.004.002. | 1050.2 | Labour | 0 | 0.0000
294452 | B1 FLOOR Slab & Beam M40PT(GGBS) | Cu.Mtrs | 795.3800 | 795.3800 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 851.3800 | 1050.2 | 150.001.001.002.002.004.005. | 1050.2 | Labour | 0 | 0.0000
294497 | B1 FLOOR M50 (GGBS)-Column | Cu.Mtrs | 353.0000 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 353.0000 | 1050.2 | 150.001.001.002.002.004.009. | 1050.2 | Labour | 0 | 0.0000
282088 | LG FLOOR RCC Labour Work | Sq.Ft | 37567.7000 | 37567.7000 | 1179 | Rcc on Area Basis | Sq.Ft | 37567.7000 | 370.52 | 150.001.001.002.002.005.001. | 370.52 | Labour | 0 | 0.0000
282088 | LG FLOOR RCC Labour Work | Sq.Ft | 37567.7000 | 37567.7000 | 2663 | RCC Pardi | Sq.Ft | 572.6000 | 370.52 | 150.001.001.002.002.005.001. | 370.52 | Labour | 0 | 0.0000
286100 | LG FLOOR M50 (GGBS) | Cu.Mtrs | 238.8200 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 244.8200 | 1050.2 | 150.001.001.002.002.005.002. | 1050.2 | Labour | 0 | 0.0000
300280 | LG FLOOR M40PT(GGBS) | Cu.Mtrs | 774.0000 | 774.0000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 844.0000 | 1050.2 | 150.001.001.002.002.005.009. | 1050.2 | Labour | 0 | 0.0000
300281 | LG FLOOR Column - M50 (GGBS) | Cu.Mtrs | 353.0310 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 64.0000 | 1050.2 | 150.001.001.002.002.005.010. | 1050.2 | Labour | 0 | 0.0000
282090 | GR FLOOR RCC Labour Work | Sq.Ft | 10705.1200 | 10705.1200 | 1179 | Rcc on Area Basis | Sq.Ft | 10705.1200 | 370.52 | 150.001.001.002.002.006.001. | 370.52 | Labour | 0 | 0.0000
301353 | GR FLOOR - Column Concrete - M50 (GGBS) | Cu.Mtrs | 451.0000 | 451.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 451.0000 | 1050.2 | 150.001.001.002.002.006.002. | 1050.2 | Labour | 0 | 0.0000
301356 | GR FLOOR - PT Slab & Beam - M40PT | Cu.Mtrs | 147.8000 | 147.8000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 147.8000 | 1050.2 | 150.001.001.002.002.006.005. | 1050.2 | Labour | 0 | 0.0000
282092 | LO 1ST FLOOR RCC Labour Work | Sq.Ft | 0.0000 | 0.0000 | 1179 | Rcc on Area Basis | Sq.Ft | 0.0000 | 370.52 | 150.001.001.002.002.007.001. | 370.52 | Labour | 0 | 0.0000
301534 | LO 1ST FLOOR M50 (GGBS) - Column | Cu.Mtrs | 214.2400 | 214.2400 | 14242 | M50 Concrete Processing | Cu.Mtrs | 214.2400 | 1050.2 | 150.001.001.002.002.007.006. | 1050.2 | Labour | 0 | 0.0000
301535 | LO 1ST FLOOR M40PT Slab & Beam | Cu.Mtrs | 75.5400 | 75.5400 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 75.5400 | 1050.2 | 150.001.001.002.002.007.007. | 1050.2 | Labour | 0 | 0.0000
282094 | 1ST FLOOR RCC Labour Work | Sq.Ft | 13173.6300 | 13173.6300 | 1179 | Rcc on Area Basis | Sq.Ft | 13173.6300 | 370.52 | 150.001.001.002.002.008.001. | 370.52 | Labour | 0 | 0.0000
282094 | 1ST FLOOR RCC Labour Work | Sq.Ft | 13173.6300 | 13173.6300 | 7508 | RCC on area basis 3.7 to 4.6 m ht | Sq.Ft | 12410.7800 | 111.16 | 150.001.001.002.002.008.001. | 111.16 | Labour | 167 | 134036.4200 | C+S GST 18% I/P RD
301540 | 1ST FLOOR M50 (GGBS) - Column | Cu.Mtrs | 214.2350 | 214.2350 | 14242 | M50 Concrete Processing | Cu.Mtrs | 214.2350 | 1050.2 | 150.001.001.002.002.008.005. | 1050.2 | Labour | 0 | 0.0000
301542 | 1ST FLOOR M40PT - Slab & Beam | Cu.Mtrs | 166.3900 | 166.3900 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 166.3900 | 1050.2 | 150.001.001.002.002.008.007. | 1050.2 | Labour | 0 | 0.0000
282096 | LO 2ND FLOOR RCC Labour Work | Sq.Ft | 0.0000 | 0.0000 | 1179 | Rcc on Area Basis | Sq.Ft | 0.0000 | 370.52 | 150.001.001.002.002.009.001. | 370.52 | Labour | 0 | 0.0000
308258 | LO 2ND FLOOR - Column M50 (GGBS) | Cu.Mtrs | 29.0000 | 29.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 29.0000 | 1050.2 | 150.001.001.002.002.009.004. | 1050.2 | Labour | 0 | 0.0000
308260 | LO 2ND FLOOR - PT Slab & Beam - M40PT | Cu.Mtrs | 77.5000 | 77.5000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 77.5000 | 1050.2 | 150.001.001.002.002.009.006. | 1050.2 | Labour | 0 | 0.0000
282098 | 2ND FLOOR RCC Labour Work | Sq.Ft | 15789.7000 | 15789.7000 | 1179 | Rcc on Area Basis | Sq.Ft | 15789.7000 | 370.52 | 150.001.001.002.002.010.001. | 370.52 | Labour | 0 | 0.0000
282098 | 2ND FLOOR RCC Labour Work | Sq.Ft | 15789.7000 | 15789.7000 | 7508 | RCC on area basis 3.7 to 4.6 m ht | Sq.Ft | 17334.2400 | 111.16 | 150.001.001.002.002.010.001. | 111.16 | Labour | 167 | 187209.7900 | C+S GST 18% I/P RD
308265 | 2ND FLOOR Column - M50 (GGBS) | Cu.Mtrs | 242.0000 | 0.0000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 242.0000 | 1050.2 | 150.001.001.002.002.010.005. | 1050.2 | Labour | 0 | 0.0000
308267 | 2ND FLOOR PT Slab & Beam - M40PT | Cu.Mtrs | 277.3000 | 277.3000 | 14240 | M40PT Concrete Processing | Cu.Mtrs | 277.3000 | 1050.2 | 150.001.001.002.002.010.007. | 1050.2 | Labour | 0 | 0.0000
282100 | 3RD FLOOR RCC Labour Work | Sq.Ft | 11867.9500 | 11867.9500 | 7508 | RCC on area basis 3.7 to 4.6 m ht | Sq.Ft | 11867.9500 | 403.19 | 150.001.001.002.002.011.001. | 403.19 | Labour | 0 | 0.0000
308281 | 3RD FLOOR Column - M50 (GGBS) | Cu.Mtrs | 383.2000 | 383.2000 | 14242 | M50 Concrete Processing | Cu.Mtrs | 383.2000 | 1050.2 | 150.001.001.002.002.011.007. | 1050.2 | Labour | 0 | 0.0000
282102 | 4TH FLOOR RCC Labour Work | Sq.Ft | 9856.1600 | 9856.1600 | 1179 | Rcc on Area Basis | Sq.Ft | 9856.1600 | 370.52 | 150.001.001.002.002.012.001. | 370.52 | Labour | 0 | 0.0000
282104 | 5TH FLOOR RCC Labour Work | Sq.Ft | 9867.1400 | 9867.1400 | 1179 | Rcc on Area Basis | Sq.Ft | 9867.1400 | 370.52 | 150.001.001.002.002.013.001. | 370.52 | Labour | 0 | 0.0000
282106 | 6TH FLOOR RCC Labour Work | Sq.Ft | 10511.4700 | 10511.4700 | 1179 | Rcc on Area Basis | Sq.Ft | 10511.4700 | 370.52 | 150.001.001.002.002.014.001. | 370.52 | Labour | 0 | 0.0000
282108 | 7TH FLOOR RCC Labour Work | Sq.Ft | 16669.6700 | 16669.6700 | 1179 | Rcc on Area Basis | Sq.Ft | 16669.6700 | 370.52 | 150.001.001.002.002.015.001. | 370.52 | Labour | 0 | 0.0000
282110 | 8TH FLOOR RCC Labour Work | Sq.Ft | 15233.2100 | 15233.2100 | 1179 | Rcc on Area Basis | Sq.Ft | 15233.2100 | 370.52 | 150.001.001.002.002.016.001. | 370.52 | Labour | 0 | 0.0000
282112 | 9TH FLOOR RCC Labour Work | Sq.Ft | 15343.6500 | 15343.6500 | 1179 | Rcc on Area Basis | Sq.Ft | 15343.6500 | 370.52 | 150.001.001.002.002.017.001. | 370.52 | Labour | 0 | 0.0000
282114 | 10TH FLOOR RCC Labour Work | Sq.Ft | 15285.7400 | 15285.7400 | 1179 | Rcc on Area Basis | Sq.Ft | 15285.7400 | 370.52 | 150.001.001.002.002.018.001. | 370.52 | Labour | 0 | 0.0000
282116 | 11TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.019.001. | 370.52 | Labour | 0 | 0.0000
282118 | 12TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.020.001. | 370.52 | Labour | 0 | 0.0000
282122 | 14TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.021.001. | 370.52 | Labour | 0 | 0.0000
282124 | 15TH FLOOR RCC Labour Work | Sq.Ft | 15288.9700 | 15288.9700 | 1179 | Rcc on Area Basis | Sq.Ft | 15288.9700 | 370.52 | 150.001.001.002.002.022.001. | 370.52 | Labour | 0 | 0.0000
282126 | 16TH FLOOR RCC Labour Work | Sq.Ft | 15229.0100 | 15229.0100 | 1179 | Rcc on Area Basis | Sq.Ft | 15229.0100 | 370.52 | 150.001.001.002.002.023.001. | 370.52 | Labour | 0 | 0.0000
282128 | 17TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.024.001. | 370.52 | Labour | 0 | 0.0000
282130 | 18TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.025.001. | 370.52 | Labour | 0 | 0.0000
282132 | 19TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.026.001. | 370.52 | Labour | 0 | 0.0000
282134 | 20TH FLOOR RCC Labour Work | Sq.Ft | 15288.9700 | 15288.9700 | 1179 | Rcc on Area Basis | Sq.Ft | 15288.9700 | 370.52 | 150.001.001.002.002.027.001. | 370.52 | Labour | 0 | 0.0000
282136 | 21TH FLOOR RCC Labour Work | Sq.Ft | 15229.0100 | 15229.0100 | 1179 | Rcc on Area Basis | Sq.Ft | 15229.0100 | 370.52 | 150.001.001.002.002.028.001. | 370.52 | Labour | 0 | 0.0000
282120 | 22TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.029.001. | 370.52 | Labour | 0 | 0.0000
282138 | 23RD FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.030.001. | 370.52 | Labour | 0 | 0.0000
282140 | 24TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.031.001. | 370.52 | Labour | 0 | 0.0000
282142 | 25TH FLOOR RCC Labour Work | Sq.Ft | 15288.9700 | 15288.9700 | 1179 | Rcc on Area Basis | Sq.Ft | 15288.9700 | 370.52 | 150.001.001.002.002.032.001. | 370.52 | Labour | 0 | 0.0000
282144 | 26TH FLOOR RCC Labour Work | Sq.Ft | 15229.0100 | 15229.0100 | 1179 | Rcc on Area Basis | Sq.Ft | 15229.0100 | 370.52 | 150.001.001.002.002.033.001. | 370.52 | Labour | 0 | 0.0000
282146 | 27TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.034.001. | 370.52 | Labour | 0 | 0.0000
282148 | 28TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.035.001. | 370.52 | Labour | 0 | 0.0000
282150 | 29TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.036.001. | 370.52 | Labour | 0 | 0.0000
282152 | 30TH FLOOR RCC Labour Work | Sq.Ft | 15288.9700 | 15288.9700 | 1179 | Rcc on Area Basis | Sq.Ft | 15288.9700 | 370.52 | 150.001.001.002.002.037.001. | 370.52 | Labour | 0 | 0.0000
282154 | 31TH FLOOR RCC Labour Work | Sq.Ft | 15229.0100 | 15229.0100 | 1179 | Rcc on Area Basis | Sq.Ft | 15229.0100 | 370.52 | 150.001.001.002.002.038.001. | 370.52 | Labour | 0 | 0.0000
282156 | 32TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.039.001. | 370.52 | Labour | 0 | 0.0000
282158 | 33TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.040.001. | 370.52 | Labour | 0 | 0.0000
282160 | 34TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.041.001. | 370.52 | Labour | 0 | 0.0000
282162 | 35TH FLOOR RCC Labour Work | Sq.Ft | 15288.9700 | 15288.9700 | 1179 | Rcc on Area Basis | Sq.Ft | 15288.9700 | 370.52 | 150.001.001.002.002.042.001. | 370.52 | Labour | 0 | 0.0000
282164 | 36TH FLOOR RCC Labour Work | Sq.Ft | 15176.4900 | 15176.4900 | 1179 | Rcc on Area Basis | Sq.Ft | 15176.4900 | 370.52 | 150.001.001.002.002.043.001. | 370.52 | Labour | 0 | 0.0000
282168 | TERRACE FLOOR RCC Labour Work | Sq.Ft | 14544.3200 | 14544.3200 | 1179 | Rcc on Area Basis | Sq.Ft | 14544.3200 | 370.52 | 150.001.001.002.002.044.001. | 370.52 | Labour | 0 | 0.0000
282170 | OHWT TOP & BTM RCC Labour Work | Sq.Ft | 4553.3800 | 4553.3800 | 1179 | Rcc on Area Basis | Sq.Ft | 4553.3800 | 370.52 | 150.001.001.002.002.045.001. | 370.52 | Labour | 0 | 0.0000
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 3422 | 12mm x 150mm Rebarring | No. | 32.0000 | 224.2 | 150.001.001.002.002.046.001. | 224.2 | Labour | 167 | 230.4000 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 3423 | 16mm x 150mm Rebarring | No. | 42.0000 | 275.9 | 150.001.001.002.002.046.001. | 275.9 | Labour | 167 | 1360.8000 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 12327 | 16mm x 200mm Rebarring | No. | 39.0000 | 365.8 | 150.001.001.002.002.046.001. | 365.8 | Labour | 167 | 1263.6000 | C+S GST 18% I/P RD
286969 | RCC Misc. Work | Per Project | 1.0000 | 1.0000 | 3421 | 8mm x 150mm Rebarring | No. | 210.0000 | 132.38 | 150.001.001.002.002.046.001. | 132.38 | Labour | 167 | 1890.0000 | C+S GST 18% I/P RD
301826 | STP M35 (GGBS) | Cu.Mtrs | 0.0000 | 0.0000 | 14238 | M35 Concrete Processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.002.002.047.002. | 1050.2 | Labour | 0 | 0.0000
301826 | STP M35 (GGBS) | Cu.Mtrs | 0.0000 | 0.0000 | 23293 | M35 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.002.002.047.002. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
301830 | M35 (GGBS)- Slab & Beam | Cu.Mtrs | 247.2550 | 247.2550 | 14238 | M35 Concrete Processing | Cu.Mtrs | 247.2550 | 1050.2 | 150.001.001.002.002.047.006. | 1050.2 | Labour | 0 | 0.0000
301830 | M35 (GGBS)- Slab & Beam | Cu.Mtrs | 247.2550 | 247.2550 | 23293 | M35 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.002.002.047.006. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
301831 | M35 (GGBS)- Column | Cu.Mtrs | 22.0000 | 22.0000 | 14238 | M35 Concrete Processing | Cu.Mtrs | 22.0000 | 1050.2 | 150.001.001.002.002.047.007. | 1050.2 | Labour | 0 | 0.0000
301831 | M35 (GGBS)- Column | Cu.Mtrs | 22.0000 | 22.0000 | 23293 | M35 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.002.002.047.007. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
314628 | UG Tank RCC Labour Work | Sq.Ft | 0.0000 | 0.0000 | 2442 | RCC OF UGWT | Ltrs | 415101.0000 | 5.9 | 150.001.001.002.002.049.003. | 5.9 | Labour | 167 | 224154.5400 | C+S GST 18% I/P RD
314628 | UG Tank RCC Labour Work | Sq.Ft | 0.0000 | 0.0000 | 1179 | Rcc on Area Basis | Sq.Ft | 0.0000 | 370.52 | 150.001.001.002.002.049.003. | 370.52 | Labour | 167 | 0.0000 | C+S GST 18% I/P RD
315004 | Basement 4 Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 1222.2400 | 35.4 | 150.001.001.002.003.001.002.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315012 | Basement 3 Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 1222.2400 | 35.4 | 150.001.001.002.003.001.003.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315030 | Basement 2 Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 1680.0000 | 35.4 | 150.001.001.002.003.001.004.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315040 | Basement 1 Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 1124.0000 | 35.4 | 150.001.001.002.003.001.005.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315048 | LG Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 3997.0000 | 35.4 | 150.001.001.002.003.001.006.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315056 | Gr Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 867.0000 | 35.4 | 150.001.001.002.003.001.007.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315063 | Gr Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 377.0000 | 35.4 | 150.001.001.002.003.001.007.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315071 | 1st Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 1087.0000 | 35.4 | 150.001.001.002.003.001.008.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315078 | 1st Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 672.0000 | 35.4 | 150.001.001.002.003.001.008.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315086 | 2nd Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 956.0000 | 35.4 | 150.001.001.002.003.001.009.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315093 | 2nd Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 861.0000 | 35.4 | 150.001.001.002.003.001.009.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315101 | 3rd Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 3258.0000 | 35.4 | 150.001.001.002.003.001.010.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315108 | 3rd Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 341.0000 | 35.4 | 150.001.001.002.003.001.010.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315116 | 4th Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 3184.0000 | 35.4 | 150.001.001.002.003.001.011.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315123 | 4th Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 430.0000 | 35.4 | 150.001.001.002.003.001.011.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315131 | 5th Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 3205.0000 | 35.4 | 150.001.001.002.003.001.012.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315138 | 5th Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 430.0000 | 35.4 | 150.001.001.002.003.001.012.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315146 | 6th Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 3184.0000 | 35.4 | 150.001.001.002.003.001.013.001.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
315153 | 6th Floor Common Work AAC Brick work 6" | Sq.Ft | 1222.2400 | 1222.2400 | 1537 | Brick Work 6" | Sq.Ft | 341.0000 | 35.4 | 150.001.001.002.003.001.013.002.006. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
314931 | Excise Office Block Work - G Floor AAC Brick work 6" | Sq.Ft | 2035.0000 | 2035.0000 | 1537 | Brick Work 6" | Sq.Ft | 2035.0000 | 35.4 | 150.001.001.002.003.002.001.003. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
314932 | Excise Office Block Work - 1st Floor AAC Brick work 6" | Sq.Ft | 1429.0000 | 1429.0000 | 1537 | Brick Work 6" | Sq.Ft | 1429.0000 | 35.4 | 150.001.001.002.003.002.002.003. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
279745 | Basement-4 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 1849.0000 | 1849.0000 | 7549 | P/F Swellable waterbar | RMT | 600.0000 | 485.34 | 150.001.001.002.004.001.002. | 485.34 | Labour | 167 | 32400.0000 | C+S GST 18% I/P RD
279745 | Basement-4 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 1849.0000 | 1849.0000 | 8998 | Scaffolding Removing | Sq.Ft | 6192.6400 | 3 | 150.001.001.002.004.001.002. | 3 | Labour | 0 | 0.0000
279747 | Basement-3 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 441.1750 | 441.1750 | 7549 | P/F Swellable waterbar | RMT | 600.0000 | 485.34 | 150.001.001.002.004.002.002. | 485.34 | Labour | 167 | 32400.0000 | C+S GST 18% I/P RD
279747 | Basement-3 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 441.1750 | 441.1750 | 8998 | Scaffolding Removing | Sq.Ft | 6192.6400 | 3 | 150.001.001.002.004.002.002. | 3 | Labour | 0 | 0.0000
282220 | Basement-2 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 557.5650 | 557.5650 | 7549 | P/F Swellable waterbar | RMT | 600.0000 | 485.34 | 150.001.001.002.004.003.001. | 485.34 | Labour | 167 | 32400.0000 | C+S GST 18% I/P RD
282220 | Basement-2 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 557.5650 | 557.5650 | 8998 | Scaffolding Removing | Sq.Ft | 6192.6400 | 3 | 150.001.001.002.004.003.001. | 3 | Labour | 0 | 0.0000
282221 | Basement-1 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 675.6900 | 675.6900 | 7549 | P/F Swellable waterbar | RMT | 600.0000 | 485.34 | 150.001.001.002.004.004.001. | 485.34 | Labour | 167 | 32400.0000 | C+S GST 18% I/P RD
282221 | Basement-1 Retaining wall waterproofing-(Sq.Mtr) | Sq.Mt | 675.6900 | 675.6900 | 8998 | Scaffolding Removing | Sq.Ft | 6192.6400 | 3 | 150.001.001.002.004.004.001. | 3 | Labour | 0 | 0.0000
310377 | UGT Waterproofing. | Sq.Ft | 32292.0000 | 32292.0000 | 12486 | Bond Coat | Sq.Ft | 32292.0000 | 23.6 | 150.001.001.002.004.005.002.001. | 23.6 | Labour | 0 | 0.0000
314983 | GF Internal Plaster Tar Plaster | Sq.Ft | 218.0000 | 218.0000 | 9383 | Tar Plaster | Sq.Ft | 218.0000 | 29.5 | 150.001.001.002.007.001.001.005. | 29.5 | Labour | 0 | 0.0000
315160 | B4 Internal Plaster Tar Plaster | Sq.Ft | 218.0000 | 218.0000 | 9383 | Tar Plaster | Sq.Ft | 0.0000 | 0.0000 | 150.001.001.002.007.003.001.001.005. | 0.0000 | Labour | 0 | 0.0000
260959 | Labour camp Foundation M20 (GGBS) | Cu.Mtrs | 12.0000 | 12.0000 | 22264 | M20 Concrete processing | Cu.Mtrs | 12.0000 | 1050.2 | 150.001.001.007.010.004. | 1050.2 | Material | 167 | 4241.2000 | C+S GST 18% I/P RD
265582 | Project Safety Work | Per Project | 0.0000 | 0.0000 | 6382 | Safety Net Fixing Charges | Sq.Ft | 6456.0000 | 3.25 | 150.001.001.009.002.001. | 3.25 | Labour | 0 | 0.0000
265582 | Project Safety Work | Per Project | 0.0000 | 0.0000 | 6597 | Safety Net Removing Charges | Sq.Ft | 6456.0000 | 1.77 | 150.001.001.009.002.001. | 1.77 | Labour | 0 | 0.0000
269216 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 5456 | Gate Removing | Sq.Ft | 28.0000 | 23.6 | 150.001.001.009.003. | 23.6 | Labour | 0 | 0.0000
269216 | Fabrication Work | Per Project | 0.0000 | 0.0000 | 13458 | Jina Repairing | Job | 1.0000 | 2242 | 150.001.001.009.003. | 2242 | Labour | 167 | 108.0000 | C+S GST 18% I/P RD
309439 | Project Security Services | Per Project | 0.0000 | 0.0000 | 9989 | Security Guards. | No. | 66.0000 | 21240 | 150.001.001.009.009.001. | 21240 | Labour | 0 | 0.0000
312750 | Machine Hiring Charges | Per Project | 0.0000 | 0.0000 | 1953 | Crane | Hour | 100.0000 | 1180 | 150.001.001.009.015.001. | 1180 | Labour | 0 | 0.0000
266795 | Project Guniting Work | Per Project | 0.0000 | 0.0000 | 11867 | P/A of Guniting work | Sq.Mt | 1726.0000 | 1994.2 | 150.001.001.010.002.001. | 1994.2 | Labour | 0 | 0.0000
309296 | STP Work - Footing - M35 (GGBS) | Cu.Mtrs | 21.7700 | 21.7700 | 14238 | M35 Concrete Processing | Cu.Mtrs | 21.7700 | 1050.2 | 150.001.001.010.002.002.005. | 1050.2 | Labour | 0 | 0.0000
309296 | STP Work - Footing - M35 (GGBS) | Cu.Mtrs | 21.7700 | 21.7700 | 23293 | M35 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.010.002.002.005. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
309297 | STP Work M35 (GGBS) | Cu.Mtrs | 247.2550 | 0.0000 | 14238 | M35 Concrete Processing | Cu.Mtrs | 247.2550 | 1050.2 | 150.001.001.010.002.002.006. | 1050.2 | Labour | 0 | 0.0000
309297 | STP Work M35 (GGBS) | Cu.Mtrs | 247.2550 | 0.0000 | 23293 | M35 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.010.002.002.006. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
309298 | STP - Column Work M35 (GGBS) | Cu.Mtrs | 85.8000 | 85.8000 | 14238 | M35 Concrete Processing | Cu.Mtrs | 85.8000 | 1050.2 | 150.001.001.010.002.002.007. | 1050.2 | Labour | 0 | 0.0000
309298 | STP - Column Work M35 (GGBS) | Cu.Mtrs | 85.8000 | 85.8000 | 23293 | M35 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.010.002.002.007. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
310931 | STP Work M20 (GGBS) | Cu.Mtrs | 15.0000 | 15.0000 | 14234 | M20 Concrete Processing | Cu.Mtrs | 15.0000 | 1050.2 | 150.001.001.010.002.002.009. | 1050.2 | Labour | 0 | 0.0000
310931 | STP Work M20 (GGBS) | Cu.Mtrs | 15.0000 | 15.0000 | 22264 | M20 Concrete processing | Cu.Mtrs | 0.0000 | 1050.2 | 150.001.001.010.002.002.009. | 1050.2 | Material | 167 | 0.0000 | C+S GST 18% I/P RD
310381 | STP & Equilization Tank Waterproofing Waterproofing. | Sq.Ft | 11840.4000 | 11840.4000 | 12486 | Bond Coat | Sq.Ft | 11840.4000 | 38.94 | 150.001.001.010.002.003.001. | 38.94 | Labour | 0 | 0.0000
294429 | External Electrical Work | Per Project | 0.0000 | 0.0000 | 8113 | Excavation In trenches (Lab) | Mtrs | 120.0000 | 230.1 | 150.001.001.010.005.001.001. | 230.1 | Labour | 0 | 0.0000
310193 | Block Work AAC Brick work 6" | Sq.Ft | 1318.4000 | 1318.4000 | 1537 | Brick Work 6" | Sq.Ft | 1318.4000 | 35.4 | 150.001.002.004.003.001.003. | 35.4 | Labour | 195 | 0.0000 | ZERO 0%
310364 | Internal Plaster Ready Mix Internal Plaster -TC | Sq.Ft | 636.1400 | 636.1400 | 9383 | Tar Plaster | Sq.Ft | 636.1400 | 29.5 | 150.001.002.004.003.003.001.001. | 29.5 | Labour | 0 | 0.0000
310365 | External Plaster Work On area basis | Sq.Ft | 1730.0000 | 1730.0000 | 2552 | Ext Plaster Area Base | Sq.Ft | 1730.0000 | 53.1 | 150.001.002.004.003.003.002.001. | 53.1 | Labour | 0 | 0.0000
310369 | Waterproofing Work Toilet W/P Work | Sq.Ft | 210.6000 | 210.6000 | 12702 | Plaster work (W/P) | Sq.Ft | 103.0000 | 38.94 | 150.001.002.004.003.004.001. | 38.94 | Labour | 0 | 0.0000
291978 | Misc Painting Work | Per Project | 0.0000 | 0.0000 | 2214 | Luster Paint | Sq.Ft | 2700.0000 | 24.78 | 150.001.002.006.001. | 24.78 | Labour | 0 | 0.0000
291978 | Misc Painting Work | Per Project | 0.0000 | 0.0000 | 7098 | P/A Apex Paint. | Sq.Ft | 16000.0000 | 15.93 | 150.001.002.006.001. | 15.93 | Labour | 167 | 48000.0000 | C+S GST 18% I/P RD
291978 | Misc Painting Work | Per Project | 0.0000 | 0.0000 | 13225 | P/A Tractor Emulsion Paint | Sq.Ft | 6500.0000 | 14.16 | 150.001.002.006.001. | 14.16 | Labour | 0 | 0.0000