## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : BRAMHACORP TOWNHOUSE B RESIDENTIAL
Task Name : Wing B1
Page 1 of 1
Total Records: 19 Records 1 to 19
Sr_No | Task | Completion_Per | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | Estimated Qty of Completed Work | Estimated Rate of Completed Work | Estimated Cost of Completed Work | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Amount | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | B1 2nd FL Internal Wall Paint | 0 | Started | Labour | (L)P/A Emulsion Paint | Sq.Ft | 4036.7 | 20 | 80734 | 0 | 0 | 0 | 0 | 20 | 0 | 2886.5563 | 15.34 | 44279.7719 | 44279.77 | 2886.5563 | 15.34 | 44279.77 | 4036.7 | 1150.1437 | 80734 | 36454.23
2 | B1 2nd FL Internal Ceiling Paint | 0 | Started | Labour | (L)P/A Premium Emulsion Paint | Sq.Ft | 1849 | 15 | 27735 | 0 | 0 | 0 | 0 | 15 | 0 | 1155.8933 | 15.34 | 17731.3929 | 17731.41 | 1155.8933 | 15.34 | 17731.41 | 1849 | 693.1067 | 27735 | 10003.59
3 | B1 2nd FL Staircase Wall & Ceiling Paint | 0 | Started | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 617.58 | 5 | 3087.9 | 0 | 0 | 0 | 0 | 5 | 0 | 308.79 | 12.98 | 4008.09 | 4008.09 | 308.79 | 12.98 | 4008.09 | 617.58 | 308.79 | 3087.9 | -920.19
4 | B1 2nd FL Staircase Railing. | 0 | Started | Labour | (L)P/A Apcolite Enamel Paint | Sq.Ft | 118.89 | 22 | 2615.58 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.89 | 118.89 | 2615.58 | 2615.58
5 | B1 2nd FL Window Grill Paint | 0 | Tentative | Labour | (L)P/A Apcolite Enamel Paint | Sq.Ft | 78.33 | 22 | 1723.26 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.33 | 78.33 | 1723.26 | 1723.26
6 | B1 2nd FL Lobby Painting Work | 0 | Tentative | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 113 | 14.76 | 1667.88 | 0 | 0 | 0 | 0 | 14.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 113 | 1667.88 | 1667.88
7 | B1 3rd FL Internal Wall Paint | 0 | Started | Labour | (L)P/A Emulsion Paint | Sq.Ft | 4036.7 | 20 | 80734 | 0 | 0 | 0 | 0 | 20 | 0 | 2886.5563 | 15.34 | 44279.7719 | 44279.77 | 2886.5563 | 15.34 | 44279.77 | 4036.7 | 1150.1437 | 80734 | 36454.23
8 | B1 3rd FL Internal Ceiling Paint | 0 | Started | Labour | (L)P/A Premium Emulsion Paint | Sq.Ft | 1849 | 15 | 27735 | 0 | 0 | 0 | 0 | 15 | 0 | 1155.8933 | 15.34 | 17731.3929 | 17731.41 | 1155.8933 | 15.34 | 17731.41 | 1849 | 693.1067 | 27735 | 10003.59
9 | B1 3rd FL Staircase Wall & Ceiling Paint | 0 | Started | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 617.58 | 5 | 3087.9 | 0 | 0 | 0 | 0 | 5 | 0 | 308.79 | 12.98 | 4008.09 | 4008.09 | 308.79 | 12.98 | 4008.09 | 617.58 | 308.79 | 3087.9 | -920.19
10 | B1 3rd FL Staircase Railing. | 0 | Started | Labour | (L)P/A Apcolite Enamel Paint | Sq.Ft | 118.89 | 22 | 2615.58 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.89 | 118.89 | 2615.58 | 2615.58
11 | B1 3rd FL Window Grill Paint | 0 | Tentative | Labour | (L)P/A Apcolite Enamel Paint | Sq.Ft | 78.33 | 22 | 1723.26 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.33 | 78.33 | 1723.26 | 1723.26
12 | B1 3rd FL Lobby Painting Work | 0 | Tentative | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 113 | 14.76 | 1667.88 | 0 | 0 | 0 | 0 | 14.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 113 | 1667.88 | 1667.88
13 | B1 4th FL Internal Wall Paint | 0 | Started | Labour | (L)P/A Emulsion Paint | Sq.Ft | 4036.7 | 20 | 80734 | 0 | 0 | 0 | 0 | 20 | 0 | 2886.5563 | 15.34 | 44279.7719 | 44279.77 | 2886.5563 | 15.34 | 44279.77 | 4036.7 | 1150.1437 | 80734 | 36454.23
14 | B1 4th FL Internal Ceiling Paint | 0 | Started | Labour | (L)P/A Premium Emulsion Paint | Sq.Ft | 1849 | 15 | 27735 | 0 | 0 | 0 | 0 | 15 | 0 | 1155.8933 | 15.34 | 17731.3929 | 17731.41 | 1155.8933 | 15.34 | 17731.41 | 1849 | 693.1067 | 27735 | 10003.59
15 | B1 4th FL Staircase Wall & Ceiling Paint | 0 | Started | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 617.58 | 5 | 3087.9 | 0 | 0 | 0 | 0 | 5 | 0 | 308.79 | 12.98 | 4008.09 | 4008.09 | 308.79 | 12.98 | 4008.09 | 617.58 | 308.79 | 3087.9 | -920.19
16 | B1 4th FL Staircase Railing. | 0 | Started | Labour | (L)P/A Apcolite Enamel Paint | Sq.Ft | 118.89 | 22 | 2615.58 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.89 | 118.89 | 2615.58 | 2615.58
17 | B1 4th FL Window Grill Paint | 0 | Tentative | Labour | (L)P/A Apcolite Enamel Paint | Sq.Ft | 78.33 | 22 | 1723.26 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.33 | 78.33 | 1723.26 | 1723.26
18 | B1 4th FL Lobby Painting Work | 0 | Tentative | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 113 | 14.76 | 1667.88 | 0 | 0 | 0 | 0 | 14.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 113 | 1667.88 | 1667.88
19 | B1 Terrace FL Staircase Ceiling Paint | 0 | Started | Labour | (L)P/A Tractor Emulsion Paint | Sq.Ft | 140 | 5 | 700 | 0 | 0 | 0 | 0 | 5 | 0 | 70.0695 | 12.98 | 909.5045 | 909.5 | 70.0695 | 12.98 | 909.5 | 140 | 69.9305 | 700 | -209.5