## Project_Work_Order6387004265139
Project Work Order
From 17 Nov 2024 To 18 Dec 2024
Page 1 of 1
Total Records: 26 Records 1 To 26
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor UG Launge Skirting | Vitrified Skirting | R.Ft | 600.84 | 23 | 13819.32 | 2487.48 | 16306.8 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 600.84 | 0 | Fixing the 600mm x 100mm skirting by cutting the vitrified tile with Cement, Grinding the cute edge with grinder to make it straight & remove the bur, filling the joints with grout, cleaning with chemical etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Umbra Patti | Fixing of Granite Umrapatti | R.Ft | 16.4 | 80 | 1312 | 236.16 | 1548.16 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 16.4 | 0 | Fixing the Granite threshold / patti at main entry door & Toilet door, EWC wall Hung ledge wall top, sliding door sill, in cement & adhesive, with necessary edge polishing etc. Complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor UG Toilet Dado | Toilet Dado Fixing | Sq.Ft | 834.39 | 24 | 20025.36 | 3604.56 | 23629.92 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 834.39 | 0 | Fixing the 600mm x 300mm Toilet wall tiles with Tile Adhesive/ Cement with or without 2mm spacer. Filling the joint with grout & cleaning the tiles with cleaning chemical before handing over & filling the joints if any remaining & replacing the damaged tiles, including all lead & lifts of the raw material from yard till work place, including necessary curing, etc. Complete |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor UG Toilet Flooring | Toilet Flooring | Sq.Ft | 26.1 | 23 | 600.3 | 108.06 | 708.36 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 26.1 | 0 | Fixing of Vetrified/Antiskid tiles 600mm x 600mm for flooring with Sand & Cement mortar bed with or without 4mm spacer as per drawing for same. Filling the joint with grout & cleaning the tiles with cleaning chemical before handing over & filling the joints if any remaining & replacing the damaged tiles , including all lead & lifts of the raw material from yard till work place, including necessary curing, applying the protection sheets or 2nd class POP over the tiles etc. Complete, removing protection sheets and cleaning with chemical before handing over the flat etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Toilet Ventilator Frame- O | Granite Window frame | R.Ft | 19.69 | 80 | 1575.2 | 283.54 | 1858.74 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 19.69 | 0 | Fixing the Toilet window frame as per the drawing including cutting & edge polishing, chamfering, pasting with Araldite, application of adhesive chemical on the pasting face of granite including Araldite supply & apply etc complete |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Granite Top for Ledge Wall | Granite Top Fixing | R.Ft | 21.88 | 75 | 1641 | 295.38 | 1936.38 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 21.88 | 0 | Charges for toilet granite ledge wall top fixing. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Toilet Door Frame- O | Toilet Granite Door Frame | R.Ft | 15.94 | 130 | 2072.2 | 373 | 2445.2 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 15.94 | 0 | Fixing the Toilet Granite Door frame as per the drawing including cutting & edge polishing, chamfering, pasting with Araldite, application of adhesive chemical on the pasting face of granite including Araldite supply & apply etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor UG Launge Border | 6" Granite Border Fixing | R.Ft | 270.9299 | 55 | 14901.14 | 2682.2 | 17583.34 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 270.9299 | 0 | Charges for common lobby boarder patti 6" In flooring work. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Entrance Granite Staircase Tread & Riser | GRANITE RISER FIXING | R.Ft | 151.5 | 60 | 9090 | 1636.2 | 10726.2 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 151.5 | 0 | Labour charges for Granite tappa fixing with champer edge polish as per instruction engineering in charge. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Entrance Landing Granite Flooring | Granite Flooring | Sq.Ft | 98 | 110 | 10780 | 1940.4 | 12720.4 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 98 | 0 | Labour charges for granite flooring in entrance including cutting, fixing as per instruction of engineering in charge. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Granite Wash Basin Counter- | Granite Basin Counter | No. | 0 | 4100 | 0 | 0 | 0 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 0 | 0 |  |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Cancelled | Ajit.p | 17 Dec 2024 | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Granite Wash Basin Counter- | Granite Basin Counter | No. | 6 | 4700 | 28200 | 5076 | 33276 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 6 | 0 | Labour charges for wash basin fixing in (Community hall & Gym ) Including cutting ,fixing with facial patti fixing full molding & champers edge polish as per instruction of engineering in charge. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Granite Sitout bench | Granite Bench | No. | 5 | 5600 | 28000 | 5040 | 33040 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 5 | 0 | Labour charges for sitout bench in club house removing & re fixing with cutting champer edge polish as per instruction of engineering incharge |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | U.G Floor Window Granite Sill Work | Granite Top Fixing | R.Ft | 240.81 | 80 | 19264.8 | 3467.66 | 22732.46 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 240.81 | 0 | Fixing the Window sills as per the drawing including cutting & edge polishing, chamfering, pasting with Araldite, application of adhesive chemical on the pasting face of granite including Araldite supply & apply etc complete |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Basement Floor Lift Lobby Border | 6" Granite Border Fixing | R.Ft | 69.02 | 50 | 3451 | 621.18 | 4072.18 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 69.02 | 0 | Charges for common lobby boarder patti 6" In flooring work. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Basement Floor Lift Lobby Granite Sill Work | Granite Top Fixing | R.Ft | 6.8055 | 80 | 544.44 | 98 | 642.44 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 6.8055 | 0 | Fixing the Granite threshold / patti at main entry door & Toilet door, EWC wall Hung ledge wall top, sliding door sill, in cement & adhesive, with necessary edge polishing etc. Complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Basement Floor Fire Lift Lobby Flooring | Vitrified Flooring | Sq.Ft | 181 | 30 | 5430 | 977.4 | 6407.4 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 181 | 0 | Fixing of Vetrified tiles 600mm x 1200mm for flooring with Sand & Cement mortar bed with or without 4mm spacer as per drawing for same. Filling the joint with grout & cleaning the tiles with cleaning chemical before handing over & filling the joints if any remaining & replacing the damaged tiles , including all lead & lifts of the raw material from yard till work place, including necessary curing, applying the protection sheets or 2nd class POP over the tiles etc. Complete, removing protection sheets and cleaning with chemical before handing over the flat etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Basement Floor Fire Lift Lobby Skirting | Vitrified Skirting | R.Ft | 34 | 28 | 952 | 171.36 | 1123.36 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 34 | 0 | Fixing the 600mm x 100mm skirting by cutting the vitrified tile with Cement, Grinding the cute edge with grinder to make it straight & remove the bur, filling the joints with grout, cleaning with chemical etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | L.G Floor Lift Lobby Border | 6" Granite Border Fixing | R.Ft | 53.3078 | 50 | 2665.39 | 479.78 | 3145.17 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 53.3078 | 0 | Charges for common lobby boarder patti 6" In flooring work. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | L.G Floor Granite Sill Work | Granite Top Fixing | R.Ft | 253.374 | 80 | 20269.92 | 3648.58 | 23918.5 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 253.374 | 0 | Labour cahrges for granite top fixing including cutting , fixing & champer edge polish as per instruction engineering incharge. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | L.G Floor lift lobby Granite Sill Work | Granite Top Fixing | R.Ft | 13.611 | 80 | 1088.88 | 196 | 1284.88 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 13.611 | 0 | Fixing the Granite threshold / patti at main entry door & Toilet door, EWC wall Hung ledge wall top, sliding door sill, in cement & adhesive, with necessary edge polishing etc. Complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | L.G Floor Fire Lift Lobby Flooring | Vitrified Flooring | Sq.Ft | 180 | 30 | 5400 | 972 | 6372 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 180 | 0 | Fixing of Vetrified tiles 600mm x 1200mm for flooring with Sand & Cement mortar bed with or without 4mm spacer as per drawing for same. Filling the joint with grout & cleaning the tiles with cleaning chemical before handing over & filling the joints if any remaining & replacing the damaged tiles , including all lead & lifts of the raw material from yard till work place, including necessary curing, applying the protection sheets or 2nd class POP over the tiles etc. Complete, removing protection sheets and cleaning with chemical before handing over the flat etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | L.G Floor Fire Lift Lobby Skirting | Vitrified Skirting | R.Ft | 25.75 | 28 | 721 | 129.78 | 850.78 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 25.75 | 0 | Fixing the 600mm x 100mm skirting by cutting the vitrified tile with Cement, Grinding the cute edge with grinder to make it straight & remove the bur, filling the joints with grout, cleaning with chemical etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Terrace Floor Fire Lift Border | 6" Granite Border Fixing | R.Ft | 48.72 | 50 | 2436 | 438.48 | 2874.48 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 48.72 | 0 | Charges for common lobby boarder patti 6" In flooring work. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Terrace Floor Fire Lift Lobby Flooring | Vitrified Flooring | Sq.Ft | 127 | 30 | 3810 | 685.8 | 4495.8 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 127 | 0 | Fixing of Vetrified tiles 600mm x 1200mm for flooring with Sand & Cement mortar bed with or without 4mm spacer as per drawing for same. Filling the joint with grout & cleaning the tiles with cleaning chemical before handing over & filling the joints if any remaining & replacing the damaged tiles , including all lead & lifts of the raw material from yard till work place, including necessary curing, applying the protection sheets or 2nd class POP over the tiles etc. Complete, removing protection sheets and cleaning with chemical before handing over the flat etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0
BramhaCorp Smart | 108 | 3 | 24 Jun 2023 | Ganesh. J. Construction | Terrace Floor Fire Lift Lobby Skirting | Vitrified Skirting | R.Ft | 34.18 | 28 | 957.04 | 172.26 | 1129.3 | 5 | 0 | 0 | -33000 | 0 | 0 | 0 | 34.18 | 0 | Fixing the 600mm x 100mm skirting by cutting the vitrified tile with Cement, Grinding the cute edge with grinder to make it straight & remove the bur, filling the joints with grout, cleaning with chemical etc complete. |  |  | rahul.m |  | CONSTRUCTION |  | CONSTRUCTION WO | Tiling | Un-Approved |  |  | 0